## WBS
ID | Activity | Description | Deliverables | Start | Finish | Duration
1 | Requirements | What does our customer need from the product? | T00, T01, T02 | 2019-08-26 | 2019-10-06 | 42
2 | Research & Design | What do we need to know in order to build our prodcut. |  | 2019-10-07 | 2019-10-27 | 21
2.1 | Existing Tools | What tools arleady exist, how do they work, and where do they fall short? | T03 | 2019-10-07 | 2019-10-13 | 7
2.2 | General Architecture | Refine required software, structures, and tools for Dev. | T04, E03 | 2019-10-14 | 2019-10-20 | 7
2.3 | Design | Define minimal viable product at each Dev. Stage. | T05 | 2019-10-21 | 2019-10-27 | 7
3 | Implementation / Coding | Creating the product. |  | 2019-10-28 | 2019-02-17 | 70
3.1 | Packer Dev. | Build packer. | T06, T07, T11 | 2019-10-28 | 2019-11-10 | 14
3.2 | Loader Dev. | Build loader. | T08, T09, E04 | 2019-11-11 | 2019-11-24 | 14
3.3 | P/L Networking Dev. | Build networking for the packer to communicate with the loader. | T10, T12 | 2019-11-25 | 2019-12-08 | 14
3.4 | P/L Networking Integration | Verification of previous development phases. | TBD | 2019-01-20 | 2019-02-02 | 14
3.5 | Deployment Mechanism Dev. | Build basic modules for deploying the packer/loader. |  | 2019-02-03 | 2019-02-16 | 14
4 | Testing & Quality Assurance (Q.A.) | Verifying the product performs as designed. |  | 2019-02-17 | 2019-03-29 | 35
4.1 | Packer Q.A. | Check packer performance. |  | 2019-02-17 | 2019-02-23 | 7
4.2 | Loader Q.A. | Check loader performance. |  | 2019-02-24 | 2019-03-01 | 7
4.3 | Networking Integration Q.A. | Check network performance. |  | 2019-03-02 | 2019-03-08 | 7
4.4 | Customer Deployment | Have customer deploy product in their enviornment for user testing. |  | 2019-03-16 | 2019-03-22 | 7
4.5 | Final Development | Final touches and packaging and workflow to meet customer requests. |  | 2019-03-23 | 2019-03-29 | 14

## Gnatt
ID | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | … | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27
1 | Requirements
2 | [6 empty] | Research & Design
2.1 | [6 empty] | 2.1 | [9 empty] | W | [6 empty] | S
2.2 | [7 empty] | 2.2 | [5 empty] | F |  |  | I | [6 empty] | P
2.3 | [8 empty] | 2.3 |  |  |  |  | A |  |  | N | [6 empty] | R
3 | [9 empty] | Implementation |  |  |  | L | Coding |  | T | More Coding | [5 empty] | I
3.1 | [9 empty] | 3.1 |  |  |  | L |  |  | E | [6 empty] | N
3.2 | [11 empty] | 3.2 |  |  |  |  | R | [6 empty] | G
3.3 | [13 empty] | B | 3.3
3.4 | [13 empty] | R |  |  | B | 3.4 | [5 empty] | B
3.5 | [13 empty] | E |  |  | R |  |  | 3.5 |  |  |  | R
4 | [13 empty] | A |  |  | E |  |  |  |  | Testing |  | E | Deployment
4.1 | [13 empty] | K |  |  | A |  |  |  |  | 4.1 |  | A
4.2 | [16 empty] | K | [5 empty] | 4.2 | K
4.3 | [24 empty] | 4.2
4.4 | [25 empty] | 4.4
4.5 | [26 empty] | 4.5

## Team Hours
| Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Avg
Andrew Chapin | 4 | 7 | 9 | 7 | 6 | 7 | 5 | 5 | 8 | [14 empty] | 6.4444
Andre Herrera | 3 | 8 | 7 | 7 | 6 | 6 | 6 | 6 | 8 | [14 empty] | 6.3333
Hunter Rowlette | 2 | 9 | 8 | 5 | 6 | 7 | 7 | 6 | 7 | [14 empty] | 6.3333
Mitch Palmer | 1 | 9 | 8 | 5 | 6 | 7 | 8 | 5 | 8 | [14 empty] | 6.3333
Carl | 1 | 8 | 9 | 7 | 6 | 6 | 7 | 6 | 9 | [14 empty] | 6.5556
Hours Worked | 11 | 41 | 41 | 31 | 30 | 33 | 33 | 28 | 40 | [14 empty] | 32
Total Hours | 11 | 52 | 93 | 124 | 154 | 187 | 220 | 248 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288