## WBS
ID | Activity | Description | Deliverables | Start | Finish | Duration
1 | Requirements | What does our customer need from the product? | T00, T01, T02 | 2019-08-26 | 2019-10-06 | 42
2 | Research & Design | What do we need to know in order to build our prodcut. |  | 2019-10-07 | 2019-10-27 | 21
2.1 | Existing Tools | What tools arleady exist, how do they work, and where do they fall short? | T03 | 2019-10-07 | 2019-10-13 | 7
2.2 | General Architecture | Refine required software, structures, and tools for Dev. | T04, E03 | 2019-10-14 | 2019-10-20 | 7
2.3 | Design | Define minimal viable product at each Dev. Stage. | T05 | 2019-10-21 | 2019-10-27 | 7
3 | Implementation / Coding | Creating the product. |  | 2019-10-28 | 2019-02-17 | 70
3.1 | Packer Dev. | Build packer. | T06, T07, T11 | 2019-10-28 | 2019-11-10 | 14
3.2 | Loader Dev. | Build loader. | T08, T09, E04 | 2019-11-11 | 2019-11-24 | 14
3.3 | P/L Networking Dev. | Build networking for the packer to communicate with the loader. | T10, T12 | 2019-11-25 | 2019-12-08 | 14
3.4 | P/L Networking Integration | Verification of previous development phases. | TBD | 2019-01-20 | 2019-02-02 | 14
3.5 | Deployment Mechanism Dev. | Build basic modules for deploying the packer/loader. |  | 2019-02-03 | 2019-02-16 | 14
4 | Testing & Quality Assurance (Q.A.) | Verifying the product performs as designed. |  | 2019-02-17 | 2019-03-29 | 35
4.1 | Packer Q.A. | Check packer performance. |  | 2019-02-17 | 2019-02-23 | 7
4.2 | Loader Q.A. | Check loader performance. |  | 2019-02-24 | 2019-03-01 | 7
4.3 | Networking Integration Q.A. | Check network performance. |  | 2019-03-02 | 2019-03-08 | 7
4.4 | Customer Deployment | Have customer deploy product in their enviornment for user testing. |  | 2019-03-16 | 2019-03-22 | 7
4.5 | Findal Development | Final touches and packaging and workflow to meet customer requests. |  | 2019-03-23 | 2019-03-29 | 14

## Gnatt
Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | … | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27
Requirements
Research & Design
[9 empty] | Implementation |  |  |  |  | Coding |  |  | More Coding
[21 empty] | Testing |  |  | Deployment

## Team Hours
| Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27
Andrew Chapin | 4 | 7 | 6 | 4 | 4 | 4 | 12 | 12 | 12 | 12 | 0 | 24 | 24 | 12 | 12 | 12 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0
Andre Herrera | 3 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 6
Hunter Rowlette | 2 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 6
Mitch Palmer | 1 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 6
Carl Bai | 1 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 6
Hours Worked | 11 | 41 | 30 | 28 | 28 | 28 | 36 | 36 | 36 | 36 | 0 | 48 | 48 | 36 | 36 | 36 | 36 | 30 | 30 | 0 | 24 | 24 | 24 | 24