## Slide 1
Project Name: Windows Packer/Loader
Team Name: BluSh3ll
Deliverables:
CLIN-1 Customer Reporting “Quad -Pack” - ?
CLIN-2 Weekly Activity/Time Sheet – Due every Friday
CLIN-3 Color Team Briefing – 9/22/19
CLIN-4 Proposal – 10/18/19
CLIN-5 Design Review Briefing – 12/1/19
CLIN-6 Poster Paper – Next Semester
CLIN-7 Encryption and Compression Design and Techniques Report – Next Semester
CLIN-8 Final Report and Team Presentation – End of Next Semester
CLIN-9 Product Specifications - ?
CLIN-10 Packer/Loader Source Code and Completed/Compiled Tool – Week 20
Key Accomplishments:
Set up and began initial development using .NET 3.5 and its namespaces in VisualStudio synced to Github repo.
Issues:
Initial delay in contacting costumer, finding ample time to meet around other exams and projects, 1 missed bi-weekly call with SME, late submissions for week 10
Schedule Status: On Schedule
Cost Status: No monetary cost, 187 Hours contributed (202 predicted)
Executive Summary
Date: 11/3/2019

## Slide 2
Critical Milestone Dates:
Return to “Green”
If issues occur this semester, we will allocate more time to work during winter break
If issues occur next semester, we will cut back on the testing and development phase to allocate more time to fix issues
Plans for Next Reporting Period:
Plans are listed in Critical Milestone section above
Issues/Future Plans
Date: 11/3/2019
ID | Activity | Description | Deliverables | Start | Finish | Duration
1 | Requirements | What does our customer need from the product? | T00, T01, T02 | 8/26/2019 | 10/6/2019 | 42
2 | Research & Design | What do we need to know in order to build our prodcut. |  | 10/7/2019 | 10/27/2019 | 21
2.1 | Existing Tools | What tools arleady exist, how do they work, and where do they fall short? | T03 | 10/7/2019 | 10/13/2019 | 7
2.2 | General Architecture | Refine required software, structures, and tools for Dev. | T04, E03 | 10/14/2019 | 10/20/2019 | 7
2.3 | Design | Define minimal viable product at each Dev. Stage. | T05 | 10/21/2019 | 10/27/2019 | 7
3 | Implementation / Coding | Creating the product. |  | 10/28/2019 | 2/17/2019 | 70
3.1 | Packer Dev. | Build packer. | T06, T07, T11 | 10/28/2019 | 11/10/2019 | 14
3.2 | Loader Dev. | Build loader. | T08, T09, E04 | 11/11/2019 | 11/24/2019 | 14
3.3 | P/L Networking Dev. | Build networking for the packer to communicate with the loader. | T10, T12 | 11/25/2019 | 12/8/2019 | 14
3.4 | P/L Networking Integration | Verification of previous development phases. | TBD | 1/20/2019 | 2/2/2019 | 14
3.5 | Deployment Mechanism Dev. | Build basic modules for deploying the packer/loader. |  | 2/3/2019 | 2/16/2019 | 14
4 | Testing & Quality Assurance (Q.A.) | Verifying the product performs as designed. |  | 2/17/2019 | 3/29/2019 | 35
4.1 | Packer Q.A. | Check packer performance. |  | 2/17/2019 | 2/23/2019 | 7
4.2 | Loader Q.A. | Check loader performance. |  | 2/24/2019 | 3/1/2019 | 7
4.3 | Networking Integration Q.A. | Check network performance. |  | 3/2/2019 | 3/8/2019 | 7
4.4 | Customer Deployment | Have customer deploy product in their enviornment for user testing. |  | 3/16/2019 | 3/22/2019 | 7
4.5 | Findal Development | Final touches and packaging and workflow to meet customer requests. |  | 3/23/2019 | 3/29/2019 | 14

## Slide 3
Schedule
Date: 11/3/2019
Comments:
- Project is on schedule; we have started implementation

## Slide 4: Customer Satisfaction Survey Date:
Customer Satisfaction
Date: 11/3/2019